# Institutional Activation Runbook

Execution order for converting the draft corpus into a live governed institution

| Document ID | ACT-RUN-001 |
| --- | --- |
| Version | 0.1.0 |
| Status | Activation Working Draft |
| Classification | Institutional Activation Runbook |
| Parent | Institutional Activation System |

Control note: Bracketed fields and unresolved constants must be verified from source evidence before adoption. Do not backdate, infer, or fabricate organizational facts.

# Gate 0 - No Fabrication

Do not mark a constant VERIFIED without evidence.

Do not treat a draft signature block as an adoption.

Do not create historical attendance, finance, credential, membership, safeguarding, or governance records retroactively to manufacture maturity.

# Gate 1 - Repository and Controls

Run scaffold_institution.py into the chosen repository root.

Place this activation pack in the canonical paths shown by the repository manifest.

Approve REPO-001 and REC-ID-001 as internal control standards.

Populate ORG-CONST-001 only from verified evidence.

Initialize the Activation Control Workbook.

# Gate 2 - Civil Formation

Finalize legal name and charter constants.

File/confirm Tennessee charter.

Confirm organizational authority.

Use BOARD-ACT-001 for the actual organizational meeting or written consent.

Obtain EIN.

Open institutional banking and establish accounting only after authorization.

# Gate 3 - Ecclesiastical Formation

Review exact versions of REL-CON-001 and ECC-CON-001.

Execute EC-FOUND-001 through the valid founding ecclesiastical process.

Start FOUND-TRANS-001 clock on actual constitutional adoption date.

Constitute only bodies for which qualified persons actually exist; mark others ADOPTED - NOT YET ACTIVATED.

# Gate 4 - Corpus Adoption

Adopt dependency-critical instruments first.

Use ADOPT-001/Activation Control Workbook to track version, authority, decision ID, concurrence, effective date and canonical path.

Produce certified PDF or signed representation when appropriate.

Move superseded drafts to 99-archive without deleting history.

# Gate 5 - Operational Activation

Activate safeguarding before youth/vulnerable-person ministries.

Activate financial controls before material funds are administered.

Activate membership only when MEM-001 and membership procedures are adopted.

Activate credentialing only when competent credential authority, records and safeguards are in place.

Begin worship/service/attendance records contemporaneously with actual operation.

# Gate 6 - Filing Readiness

Quarterly compare actual evidence to CH-053 church-characteristics matrix.

Replace CH-049/050 placeholders only with verified facts.

Assemble final supplemental attachment from actual canonical evidence.

Obtain legal/tax review appropriate to filing risk and submit only when representations are true as of filing.

# Adoption and Certification

| Field | Entry |
| --- | --- |
| Organization | [[CORP_NAME]] |
| Version | 1.0.0 upon adoption |
| Date of Adoption | [[DATE]] |
| Adopting Authority | [[ADOPTING_AUTHORITY]] |
| Decision / Resolution ID | [[DECISION_ID]] |
| Effective Date | [[EFFECTIVE_DATE]] |
| Canonical Repository Path | [[PATH]] |

Certification: I certify that the foregoing instrument was duly adopted or approved as stated above and that this certified copy is the canonical institutional copy unless superseded through valid process.

________________________________________
[[NAME / OFFICE]]
[[DATE]]